## Sheet1
Key | Folder | Parent task | Title | Status | Priority | Assigned To | Start Date | Time Spent (Hours) | End Date | Description
2 | / | Planning | Create Project Plan | Active | Normal | Everyone | 2022-10-09 | 1 hour | 2022-10-23 | We all had seperate ideas as far as what we wanted to implement but we eventually kind of made a pro con list on what would be the coolest and challenging enough but not too hard to accomplish and it was an online pizza ordering system.
3 | / | Planning | Team Assignment | Active | Normal | Savannah | 2022-10-09 | 1 hour | 2022-10-23 | We all talked and just talked about our plan for for the project this zoom was combined with others talks and took around an hour
4 | / | Planning | Role Assignment | Active | Normal | Savannah | 2022-10-09 | .5 hours | 2022-10-09 | I took the project manager roll, claira took analyst, mason took technical leader, and jose to project sponsor. Through out the project though we all helped each other and our rolls all clashed, but it helped us finish the project in the end
5 | / | Planning | Propose Project | Active | Normal | Mason | 2022-10-09 | .5 Hours | 2022-10-09 | I proposed this idea in my project proposal to the team and we all agreed that this seemed like a really interesting and challenging project.
6 | / | Planning | Get Approval For Project | Active | Normal | Everyone | 2022-10-09 | .5 hours | 2022-10-23 | Our proposal was approved right away and we were able to start ironing out some details.
7 | / | Planning | Select Development Methodology | Active | Normal | Everyone | 2022-10-09 | .5 hours | 2022-10-23 | Visual studio 2022 and C#
8 | / | Planning | Feasibility Study | Active | Normal | Everyone | 2022-10-09 | .5 hous | 2022-10-23 | We knew the project was feasable we were unsure on how much time some of the tasks could possibly take because we could run into issues.
10 | / | Design | High-Level Design | Active | Normal | Everyone | 2022-10-15 | 1.5 hours | 2022-11-06 | This took a little longer just because we knew if we took our time with the high level design the implementation phase would be easier.
11 | / | Design / High-Level Design | Security Design | Active | Normal | Claira | 2022-10-15 | 2 hours | 2022-11-06 | Looked into how the information that is submitted should be entered in.
12 | / | Design / High-Level Design | User Interface Design | Active | Normal | Savannah | 2022-10-15 | .5 hours | 2022-11-06 | Claira and I had talked about our design idea together and she did focus on the design piece, but took my ideas into consideration as I was focusing on the buttons and start order piece
13 | / | Design / High-Level Design | Interfaces | Active | Normal | Mason | 2022-10-15 | 1 hour | 2022-11-06 | Designing this was interesting because there is so many different objects and examples out there so I brainstormed and decided to go with a vertical interface with checkboxes.
14 | / | Design / High-Level Design / Interfaces | External | Active | Normal | Mason | 2022-10-15 | .5 hour | 2022-11-06 | This was tricky to think about because I knew that we might run into an issue with actaully making the textboxes function but it was good to think ahead.
15 | / | Design / High-Level Design / Interfaces | Internal | Active | Normal | Jose | 2022-10-15 | 1 hour | 2022-11-06 | I was able to store the textboxes that were checked in order to make sure only one box was selected.
16 | / | Design / High-Level Design | Architecture | Active | Normal | Claira | 2022-10-15 | 1 hour | 2022-11-06 | We were deciding on how the project should look and work. We also decided on what we are using to make the project.
17 | / | Design / High-Level Design | Database Design | Active | Normal | Claira | 2022-10-15 | 2 hours | 2022-11-06 | We have a database for the pizza being ordered. Didn't have time to implement a database for users. I made a diagram for the database design
18 | / | Design / High-Level Design | Design Diagrams | Active | Normal | Claira | 2022-10-15 | 1 hour | 2022-11-06 | We all added a bit to the design digrams that are listed below.
19 | / | Design / High-Level Design / Design Diagrams | Class Diagrams | Active | Normal | Mason | 2022-10-15 | 1 hour | 2022-11-06 | I was able to create my class diagrams and show the relationships between the classes and things that inherit from eachother such as the ingedients and the store.
20 | / | Design / High-Level Design / Design Diagrams | Data Flow Diagrams | Active | Normal | Savannah | 2022-10-15 | 1 hour | 2022-11-06 | WIth the data flow it was fairly easy as we went through the start order using buttons and pushed that onto the next page (cart) and then pushed that onto the final page of payment
21 | / | Design / High-Level Design / Design Diagrams | Activity Diagrams | Active | Normal | Jose | 2022-10-15 | .5 hours | 2022-11-06 | The activity diagram shows how a customer will navigate through our site to order a pizza.
22 | / | Design / High-Level Design / Design Diagrams | Use Case Diagrams | Active | Normal | Savannah | 2022-10-15 | .5 hours | 2022-11-06 | I had made a few user stories an example of one was customer places order and is able to pay online with credit
23 | / | Design | Low-Level Design | Active | Normal | Everyone | 2022-10-15 | 1 hour | 2022-11-06 | The low level design went very smoothly as we all worked very closely on it and communicated well.
25 | / | Implementation | User Interface | Active | Normal | Mason | 2022-11-08 | 1 hour | 2022-11-19 | This was not as bad as I thought it was going to be to implement because the checkboxes and the buttons went quite smoothly. The picture formatting was a little tricky but once I got the hang of it that went smoothly too.
27 | / | Implementation | Business Logic Layer | Active | Normal | Mason | 2022-11-08 | .5 hours | 2022-11-19 | This task was more about implementing the right ingredients a store would have and then the customer is able to navigate pages to get to eventually checkout.
28 | / | Implementation | Integration | Active | Normal | Claira | 2022-11-08 | Through whole project | 2022-11-19 | We used github to make it so that we can great the code and push it out for others to see and work with.
29 | / | Implementation | Continuous Integration | Active | Normal | Savannah | 2022-11-08 | Through whole project | 2022-11-19 | I use integration through the whole project with continous testing as I created new buttons and worked onto getting all the information on the next page. This is a process I and we all constantly used
30 | / | Implementation | Bug Tracking | Active | Normal | Claira | 2022-11-08 | Through whole project | 2022-11-19 | We would let each other know when there was a bug. We didn't figure out how to use a bug tracker app
31 | / | Implementation | Version Control Setup | Active | Normal | Savannah | 2022-11-08 | .5 hours | 2022-11-19 | I set up a github respository for us to use as our version control, and I actually ended up having to make another one since I moved everything into a different web forms that was easier for us to understand and use
32 | / | Implementation | Setup Test Environment | Active | Normal | Claira | 2022-11-08 | 1 hour | 2022-11-19 | We had each other test out the project. I had a person test how the project works.
34 | / | Analysis | Legal Requirements | Active | Normal | Jose | 2022-11-19 | .5 hour | 2022-12-01 | The legal requirements went smoothly and I was able to complete them in a timely manner.
35 | / | Analysis | User Requirements | Active | Normal | Savannah | 2022-11-19 | 1 hour | 2022-12-01 | The user should be able to pick what type of pizza they want to order and pay online for pickup (size, toppings, crust type, sauce, cheese, and specialty pizzas
36 | / | Analysis | Data Requirements | Active | Normal | Mason | 2022-11-19 | .5 hours | 2022-12-01 | Our system does not deal with this too much it just specifies what kind of pizza and what toppings need to be on it and then relays it to the actual store to make the pizza.
37 | / | Analysis | Security Requirements | Active | Normal | Claira | 2022-11-19 | 2 hours | 2022-12-01 | I looked into how to make the program more secure. Ran into the issue of not having enough knownedgle and time to make a back end for the security aspect.
39 | / | Analysis | Validation and Verification of Requirements | Active | Normal | Jose | 2022-12-02 | 2 | 2022-12-10 | Messed around and researched what entries should and shouldn't be allowed. In the end, all is in order and working.
40 | / | Analysis | Submit Requirements for Approval | Active | Normal | Savannah | 2022-11-19 | .5 hours | 2022-12-01 | I submited the requirments October 23rd
41 | / | Analysis | Sign Off On Requirements | Active | Normal | Jose | 2022-12-02 | 2 | 2022-11-07 | Only form of sign in/off is the check out where email is entered.
42 | / | Analysis | Requirements From Existing System | Active | Normal | Mason | 2022-11-19 | .5 hours | 2022-12-01 | We explored other online pizza ordering systems in order to see what we liked and what we didn't in order to try and perfect ours.
43 | / | Analysis | Common Requirements | Active | Normal | Claira | 2022-11-19 | 1 hour | 2022-12-01 | We looked into what the pizza odering systems should look like.
44 | / | Analysis | Interface Requirements | Active | Normal | Mason | 2022-11-19 | 0.25 | 2022-12-01 | Our system does not need to interact with another system it just relays what was ordered on the pizza to the store.
45 | / | Analysis | Implementation Requirements | Active | Normal | Mason | 2022-11-19 | 0.5 | 2022-12-01 | Implementing what was needed as far as the user interface and what was required for a pizza company to actually be able to adopt this system possibility.
46 | / | Analysis | Prioritize Requirements (MoSCoW) | Active | Normal | Everyone | 2022-10-09 | <1 | 2022-12-10 | We all sat down during out meetings and figured out what was need and what could be done to keep it all realistic.
47 | / | Analysis | Check Requirements | Active | Normal | Savannah | 2022-11-19 | Through project | 2022-12-01 | I was constantly checking the requirements we wanted to meet to please the user and to make sure everything flowed properly
48 | / | Analysis / Check Requirements | Clear | Active | Normal | Jose | 2022-11-19 | .5 hours | 2022-12-01 | The clear requirements helped us make sure the final product would be exactly how we made it
49 | / | Analysis / Check Requirements | Unambiguous | Active | Normal | Mason | 2022-11-19 | .25 hours | 2022-12-01 | We do not have things in our system that have different meanings.
50 | / | Analysis / Check Requirements | Consistent | Active | Normal | Savannah | 2022-11-19 | 8 hours | 2022-12-01 | I put the time estimate of 8 hours as I remember going through the process to make sure all the buttons were consistent and moving onto the next page. I also made sure as a user clicks buttons and move onto the next page that was consistent too
51 | / | Analysis / Check Requirements | Prioritized | Active | Normal | Claira | 2022-11-19 | Through out the whole project | 2022-12-01 | We wanted to make sure that most important parts of the program are created and completed first.
52 | / | Analysis / Check Requirements | Verifiable | Active | Normal | Jose | 2022-11-19 | .5 hours | 2022-12-01 | The verifiable part of the project was good and I had to make sure the card and order was verified.
53 | / | Overall Testing | Testing | Active | Normal | Everyone | 2022-11-19 | Through the whole project | 2022-12-11 | We have all been doing individual testing through the whole project to make sure this works smoothly
54 | / | Testing | UI Testing | Active | Normal | Savannah | 2022-11-19 | through the whole project | 2022-12-11 | I have been doing this type of testing through the duration of the project as I mainly focused on the start order piece. There was a lot of struggle with figuring outthe buttons and checkboxes (which I ended up not using) but overall this is very easy for a user to use, but a disadvantage is that only one pizza can be ordered at a time
55 | / | Testing | Acceptance Testing | Active | Normal | Jose | 2022-11-19 | .5 hours | 2022-12-11 | This testing was good and our project met the requirements
56 | / | Testing | Unit Testing | Active | Normal | Claira | 2022-11-19 | Through the whole project | 2022-12-11 | We have been doing this throughout the entirety of the project because when we changed code others tested to see if it is user friendly.
57 | / | Testing | Regression Testing Plan | Active | Normal | Mason | 2022-11-19 | .5 hours | 2022-12-11 | We have been doing this throughout the entirety of the project like when someone made a change in the project everyone would do a pull to see if it worked good.
58 | / | Maintenance | What kind of time resources are we devoting to maintenance? | Active | Normal | Jose | 2022-11-21 | N/A | 2022-12-12 | We are devoting as much as we need for maintenence which shouldn't be much other than maybe some updates in the future.
59 | / | Maintenance | When will the next "version" be released? | Active | Normal | Jose | 2022-11-21 | N/A | 2022-12-12 | The next version would probably be realeased around 5 months from now depending on how this one does.
60 | / | Maintenance | Product Roadmap | Active | Normal | Jose | 2022-11-21 | 1 hour | 2022-12-12 | We defined what needed to be done in order to be ready for deployment on time.
62 | / | Deployment | Deployment Plan | Active | Normal | Everyone | 2022-12-11 | 1 hour | 2022-12-12 | Our deployment plan is after we make all the extra changes that would need to be made then we could introduce this cite to businesses that needed it.
64 | / | Wrap-Up | Lessons Learned Meeting | Active | Normal | Everyone | 2022-12-11 | 1 hour | 2022-12-12 | When having our final meeting and discussing we learned one of our strongest suits as a whole was our communication with eachother. We also talked a lot about how our timing was with this project. We decided that learning something new is very fun and was cool to expereince it first hand, but we definitely did not give ourselves enough time to learn what we needed to learn.
65 | / | Wrap-Up | Next Steps for Project | Active | Normal | Everyone | 2022-12-11 | 1 hour | 2022-12-12 | After speaking as a team our next step would be to allow customers to order more than one pizza, and to look into the security piece more so we could make this a functional website to be used
66 | / | Wrap-Up | Peer Reviews | Active | Normal | Everyone | 2022-12-11 | On everyone's own time | 2022-12-12 | Completed